## Project Management Plan 2022-20
Week Number | Week (DD/MM/YYYY) | Quarter Goal | Year Goal | Work Component | Difficulty
1 | 2022-08-08 | Q3: Working and Functioning CI/CD Pipeline in Azure, that deploys an Azure Flask webapp providing Boston Housing Price Prediction based on input parameters, given in a POST request. Setup Github Actions and Azure Pipelines for the Webapp. | 2022: Working CI/CD Azure Pipeline App with well documented, platform independent code | Update Documents, Setup Trello Board | Easy
2 | 2022-08-15 |  |  | Update README, Clone Project Starter Code | Easy
3 | 2022-08-22 |  |  | Starter Flask App | Easy
4 | 2022-08-29 |  |  | Test App | Easy
5 | 2022-09-05 |  |  | Add Tests | Easy
6 | 2022-09-12 |  |  | Edit Makefile tests | Easy
7 | 2022-09-19 |  |  | Add Linting | Easy
8 | 2022-09-26 |  |  | Fix any linting issues | Moderate
9 | 2022-10-03 | Q4: Add and update documentation, requirements.txt and add screenshots of working app. Add code walkthrough, outlining steps and install older versions of Python 3.7 on Azure Shell. |  | Standardize python versions | Moderate
10 | 2022-10-10 |  |  | Configure Azure Pipelines Service Principal | Moderate
11 | 2022-10-17 |  |  | Deploy Flask App, Update Readme and Trello Tasks | Easy
12 | 2022-10-24 |  |  | Review README, code and other issues | Easy
13 | 2022-10-31 |  |  |  | Easy
14 | 2022-11-07 |  |  | Research Minikube deployments on Azure App Service | Hard
15 | 2022-11-14 |  |  | Configure Minikube installation in Script | Hard
16 | 2022-11-21
17 | 2022-11-28
18 | 2022-12-05
19 | 2022-12-12
20 | 2022-12-19
21 | 2022-12-26
22 | 2023-01-02 | Q1: Add NodeJS version of code, add Kubernetes deployment for Flask App. Add gunicorn to handle multi-threading. | 2023: Upgraded version of ML Prediction WebApp, faster response times and multi-threaded.
23 | 2023-01-09
24 | 2023-01-16
25 | 2023-01-23
26 | 2023-01-30
|  |  |  | Goals | Extended Goals
|  |  |  | ML Webapp Deployed on Azure | Deploy webapp with nodeJS
|  |  |  | Build Webapp in Dockerfile | Attempt minikube deployment
|  |  |  | Configure GitHub Actions | Add Different Prediction Models

## Final Project Management Plan 2
Week Number | Week (DD/MM/YYYY) | Quarter Goal | Year Goal | Work Component | Difficulty
1 | 2022-08-08 | Q3: Working and Functioning CI/CD Pipeline in Azure, that deploys an Azure Flask webapp providing Boston Housing Price Prediction based on input parameters, given in a POST request. Setup Github Actions and Azure Pipelines for the Webapp. | 2022: Working CI/CD Azure Pipeline App with well documented, platform independent code | Update Documents, Setup Trello Board | Easy
2 | 2022-08-15 |  |  | Update README, Clone Project Starter Code | Easy
3 | 2022-08-22 |  |  | Starter Flask App | Easy
4 | 2022-08-29 |  |  | Test App | Easy
5 | 2022-09-05 |  |  | Add Tests, Edit Makefile tests | Hard
6 | 2022-09-12 |  |  | Add Linting, Suppress Warnings | Hard
7 | 2022-09-19 |  |  | Add Load Tests via Locust | Moderate
8 | 2022-09-26 |  |  | Automate Installation and Configuration of VM | Hard
9 | 2022-10-03 | Q4: Add and update documentation, requirements.txt and add screenshots of working app. Add code walkthrough, outlining steps and install older versions of Python 3.7 on Azure Shell. |  | Standardize python versions | Hard
10 | 2022-10-10 |  |  | Configure Azure Pipelines Service Principal | Easy
11 | 2022-10-17 |  |  | Automate start of webapp server and setup credentials | Easy
12 | 2022-10-24 |  |  | Complete Documentation Tasks | Easy
13 | 2022-10-31
14 | 2022-11-07
15 | 2022-11-14
16 | 2022-11-21
17 | 2022-11-28
18 | 2022-12-05 |  |  | Research Minikube deployments on Azure App Service | Hard
19 | 2022-12-12 |  |  | Configure Minikube installation in Script | Hard
20 | 2022-12-19
21 | 2022-12-26
22 | 2023-01-02 | Q1: Add NodeJS version of code, add Kubernetes deployment for Flask App. Add gunicorn to handle multi-threading. | 2023: Upgraded version of ML Prediction WebApp, faster response times and multi-threaded.
23 | 2023-01-09
24 | 2023-01-16
25 | 2023-01-23
26 | 2023-01-30
|  |  |  | Goals | Extended Goals
|  |  |  | ML Webapp Deployed on Azure | Deploy webapp with nodeJS
|  |  |  | Build Webapp in Dockerfile | Attempt minikube deployment
|  |  |  | Configure GitHub Actions | Add Different Prediction Models